## MS Planner — HMS
🏥 MS Planner — AI-Powered Hospital Management System
Bucket | # | Task Name | Assignee | Label | Priority | Due | Notes | Checklist
PRODUCT BACKLOG · 4 major tasks
Product Backlog | 1 | Implement SHAP TreeExplainer (full XAI) | Backend Dev | ML/AI | High | Apr 15 | Replace proxy XAI with real SHAP force plots | ☐ Replace proxy explainability with shap.TreeExplainer(model) ☐ Serialise SHAP output as JSON for frontend
Product Backlog | 2 | Role-based access control (Admin/Doctor/Nurse) | Full Stack | Security | High | Apr 20 | Supabase RLS + FastAPI roles | ☐ Add role column to users metadata ☐ Write RLS policies for Admin, Doctor, Nurse
Product Backlog | 3 | Real-time updates via Supabase Realtime | Frontend Dev | Frontend | Medium | Apr 25 | Replace polling with ws subscriptions | ☐ Remove existing polling from Patient & Room pages ☐ Set up supabase.channel() subscription for state updates
Product Backlog | 4 | CI/CD pipeline with GitHub Actions | DevOps | DevOps | Medium | Apr 28 | Auto-deploy FastAPI to Render + Vite to Vercel | ☐ Create deploy workflow for backend ☐ Create deploy workflow for frontend
SPRINT BACKLOG · 4 major tasks
Sprint Backlog | 1 | Fix patient_models.py heuristic bug | Backend Dev | Backend | Critical | Mar 30 | Models skipping predictions | ☐ Remove `pass` statements in try blocks ☐ Verify fallback logic behavior
Sprint Backlog | 2 | Pytest suite for hospital_predictions.py | Backend Dev | Testing | High | Apr 02 | Test core fastAPI endpoints | ☐ Write unit tests for /predict/los and /predict/demand ☐ Test 422 validations for bad inputs
Sprint Backlog | 3 | Standardise API response casing | Backend Dev | Backend | Medium | Apr 01 | Convert to camelCase | ☐ Apply generic camelCase alias_generator in pydantic ☐ Update frontend fetch expectations
Sprint Backlog | 4 | Update README for ML pipeline setup | ML Engineer | Documentation | Medium | Apr 04 | Document environment instructions | ☐ Add steps for Python venv, requirements, node setup ☐ Document env vars needed for supabase and models
IN PROGRESS · 3 major tasks
In Progress | 1 | ML Metrics dashboard polishing | Frontend Dev | Frontend | High | Mar 29 | Improve K-Fold comparison charts UI | ☐ Add dropdown to select model (XGBoost/RF) ☐ Add Recharts tooltip for exact metric values
In Progress | 2 | Performance profiling training scripts | ML Engineer | ML/AI | Medium | Mar 30 | Speed up cross-validation | ☐ Implement joblib Parallel(n_jobs=-1) in los_train.py ☐ Document speedup results
In Progress | 3 | PatientPrediction.jsx UX improvements | Frontend Dev | Frontend | Medium | Mar 30 | Smooth transition of results | ☐ Implement skeleton loader during fetch ☐ Add form validation feedback
TESTING/COMPLETED · 6 major tasks
Testing/Completed | 1 | Supabase Auth Integration | Full Stack | Security | High | Mar 13 | Login persistence across system | ✅ Session persisted via AuthContext & localStorage
Testing/Completed | 2 | Database Schema & RLS | Backend Dev | Database | High | Mar 13 | Setup patients, rooms, equipment tables | ✅ Tables created and schema committed out to SQL ✅ Basic RLS configurations validated
Testing/Completed | 3 | Core Frontend CRUD Modules | Frontend Dev | Frontend | High | Mar 18 | Pages for Inventory, Patients, Rooms | ✅ Search & filter capabilities enabled ✅ Sub-components implemented for modular UI
Testing/Completed | 4 | ML Predictor Models Trained | ML Engineer | ML/AI | High | Mar 22 | LOS, Equipment Failure, Medicine Demand | ✅ XGBoost & Prophets models persisted to .pkl ✅ Model metrics extracted and stored in JSON
Testing/Completed | 5 | Vision Anomaly Models | ML Engineer | ML/AI | High | Mar 24 | CNN Autoencoder and HF pipeline | ✅ MRI Image processing pipeline integrated ✅ Brain tumor pipeline dynamically served
Testing/Completed | 6 | Parallel API refactor | Frontend Dev | Performance | High | Mar 27 | Load time enhancement | ✅ Converted sequential API grabs to Promise.all()
TOTAL MAJOR TASKS: 17 · TOTAL CHECKLIST ITEMS: 32

## Legend
Legend
☐ Open task
✅ Completed