## Sprint 1 Retro
Sprint Retrospective
Project: AI-Powered Hospital Management System ¦ Sprint 1 ¦ Duration: 3 Weeks (06 Mar 2026 – 27 Mar 2026) ¦ Date: 27 March 2026
| What Went Well ✅ | What Went Poorly ❌ | What Ideas Do You Have 💡 | How Should We Take Action 🚀 | Guidelines
| This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
1 | ✅ Full-stack integration (React ↔ FastAPI ↔ Supabase) delivered end-to-end data flow within the first week. | ❌ Real-world healthcare data was unavailable; synthetic data introduced unrealistic patterns that affected model generalisation. | 💡 Source a real, anonymised hospital dataset (e.g., MIMIC-III) to improve model validity and academic credibility. | 🚀 Improve ML model accuracy: source better data, add cross-validation, and document evaluation metrics formally.
2 | ✅ ML models (Random Forest, XGBoost, Logistic Regression) trained and deployed via FastAPI; predictions visible in the UI. | ❌ XGBoost hyperparameter tuning was time-consuming; grid-search runs locked the notebook kernel for extended periods. | 💡 Implement full SHAP explainability using TreeExplainer for Random Forest and XGBoost models. | 🚀 Complete SHAP integration — resolve library conflicts and add SHAP force plots to the AI Insights dashboard.
3 | ✅ Prophet model successfully integrated for patient arrival forecasting with trend & seasonality decomposition. | ❌ Frontend–ML API integration issues arose due to mismatched JSON response schemas (snake_case vs camelCase). | 💡 Add Optuna-based automated hyperparameter optimisation to reduce manual tuning overhead. | 🚀 Standardise API contracts: create shared Pydantic schemas and update frontend API service layer accordingly.
4 | ✅ Interactive dashboards built with Recharts — KPI cards, sparklines, and trend charts rendered from live API data. | ❌ Full SHAP explainability (SHAP TreeExplainer) could not be completed within the sprint due to library version conflicts and time constraints. | 💡 Standardise API response schemas with a shared Pydantic base model and a camelCase serialiser on the FastAPI side. | 🚀 Implement high-risk patient alerts with email/in-app notifications using Supabase Edge Functions.
5 | ✅ Explainable AI layer implemented with feature-importance proxies surfaced in the AI Insights page. | ❌ Debugging FastAPI dependency injection errors (missing Pydantic validators) cost nearly a full day. | 💡 Introduce a CI/CD pipeline (GitHub Actions) to auto-deploy backend and run regression tests on each push. | 🚀 Expand dashboard analytics: add cohort analysis, bed-occupancy heatmap, and equipment failure trend charts.
6 | ✅ Parallel API calls (Promise.all) refactored across all pages, eliminating sequential load-time bottlenecks. | ❌ Supabase RLS (Row-Level Security) policies caused unexpected 403 errors during initial integration testing. | 💡 Add real-time data update support using Supabase Realtime subscriptions instead of polling. | 🚀 Add authentication security improvements: JWT token refresh, role-based access control (Admin / Doctor / Nurse).
7 | ✅ Supabase feedback loop established to capture prediction feedback for future model retraining. | ❌ Prophet model required significant pre-processing (datetime indexing, frequency alignment) that was underestimated in planning. | 💡 Create a high-risk patient alert system that triggers notifications when model confidence exceeds a threshold. | 🚀 Write unit & integration tests for explainability.py, patient_models.py, and all FastAPI endpoints.
8 | ✅ Task division among team members was clear; daily stand-up notes kept everyone aligned. | ❌ UI responsiveness on smaller screen sizes was inconsistent — media queries were incomplete at the end of the sprint. | 💡 Refactor frontend into smaller, reusable components to improve maintainability and test coverage. | 🚀 Fix UI responsiveness issues — apply consistent CSS Grid / Flexbox breakpoints across all pages.
9 | ✅ CORS, authentication headers, and environment variables configured correctly from day one, avoiding late-stage deployment issues. |  |  | 🚀 Document the ML pipeline, data schema, and API contracts in a project Wiki / README.

## Full Report
Sprint Retrospective Report
AI-Powered Hospital Management System (React + FastAPI + Supabase + ML)
Sprint Sprint 1 ¦ 3 Weeks (06 Mar 2026 – 27 Mar 2026) ¦ 27 March 2026
1. Sprint Overview
• Sprint Number : Sprint 1
• Duration : 3 Weeks (06 Mar 2026 – 27 Mar 2026)
• Reporting Date : 27 March 2026
• Team : Full-stack development team (React + FastAPI + ML)
• Sprint Goal :
• Build core Hospital Management System features (Patient, Room, Equipment modules)
• Integrate ML models — Random Forest, XGBoost, Logistic Regression, Prophet
• Develop AI Insights dashboard with Length-of-Stay, Readmission & Forecast predictions
• Add model evaluation metrics (accuracy, AUC, RMSE) and Explainable AI (feature importance)
• Establish Supabase backend with synthetic data pipeline and FastAPI REST layer
2. What Went Well ✅
• ✅ Full-stack integration (React ↔ FastAPI ↔ Supabase) delivered end-to-end data flow within the first week.
• ✅ ML models (Random Forest, XGBoost, Logistic Regression) trained and deployed via FastAPI; predictions visible in the UI.
• ✅ Prophet model successfully integrated for patient arrival forecasting with trend & seasonality decomposition.
• ✅ Interactive dashboards built with Recharts — KPI cards, sparklines, and trend charts rendered from live API data.
• ✅ Explainable AI layer implemented with feature-importance proxies surfaced in the AI Insights page.
• ✅ Parallel API calls (Promise.all) refactored across all pages, eliminating sequential load-time bottlenecks.
• ✅ Supabase feedback loop established to capture prediction feedback for future model retraining.
• ✅ Task division among team members was clear; daily stand-up notes kept everyone aligned.
• ✅ CORS, authentication headers, and environment variables configured correctly from day one, avoiding late-stage deployment issues.
3. What Didn't Go Well ❌
• ❌ Real-world healthcare data was unavailable; synthetic data introduced unrealistic patterns that affected model generalisation.
• ❌ XGBoost hyperparameter tuning was time-consuming; grid-search runs locked the notebook kernel for extended periods.
• ❌ Frontend–ML API integration issues arose due to mismatched JSON response schemas (snake_case vs camelCase).
• ❌ Full SHAP explainability (SHAP TreeExplainer) could not be completed within the sprint due to library version conflicts and time constraints.
• ❌ Debugging FastAPI dependency injection errors (missing Pydantic validators) cost nearly a full day.
• ❌ Supabase RLS (Row-Level Security) policies caused unexpected 403 errors during initial integration testing.
• ❌ Prophet model required significant pre-processing (datetime indexing, frequency alignment) that was underestimated in planning.
• ❌ UI responsiveness on smaller screen sizes was inconsistent — media queries were incomplete at the end of the sprint.
4. What Can Be Improved 🔧
• 💡 Source a real, anonymised hospital dataset (e.g., MIMIC-III) to improve model validity and academic credibility.
• 💡 Implement full SHAP explainability using TreeExplainer for Random Forest and XGBoost models.
• 💡 Add Optuna-based automated hyperparameter optimisation to reduce manual tuning overhead.
• 💡 Standardise API response schemas with a shared Pydantic base model and a camelCase serialiser on the FastAPI side.
• 💡 Introduce a CI/CD pipeline (GitHub Actions) to auto-deploy backend and run regression tests on each push.
• 💡 Add real-time data update support using Supabase Realtime subscriptions instead of polling.
• 💡 Create a high-risk patient alert system that triggers notifications when model confidence exceeds a threshold.
• 💡 Refactor frontend into smaller, reusable components to improve maintainability and test coverage.
5. Action Items for Next Sprint 🚀
• 🚀 Improve ML model accuracy: source better data, add cross-validation, and document evaluation metrics formally.
• 🚀 Complete SHAP integration — resolve library conflicts and add SHAP force plots to the AI Insights dashboard.
• 🚀 Standardise API contracts: create shared Pydantic schemas and update frontend API service layer accordingly.
• 🚀 Implement high-risk patient alerts with email/in-app notifications using Supabase Edge Functions.
• 🚀 Expand dashboard analytics: add cohort analysis, bed-occupancy heatmap, and equipment failure trend charts.
• 🚀 Add authentication security improvements: JWT token refresh, role-based access control (Admin / Doctor / Nurse).
• 🚀 Write unit & integration tests for explainability.py, patient_models.py, and all FastAPI endpoints.
• 🚀 Fix UI responsiveness issues — apply consistent CSS Grid / Flexbox breakpoints across all pages.
• 🚀 Document the ML pipeline, data schema, and API contracts in a project Wiki / README.
6. Key Learnings 🧠
• 🧠 Clean, well-labelled data is the single most important prerequisite for reliable ML predictions — model quality is bounded by data quality.
• 🧠 Deploying ML models in a web context requires careful API contract design; schema mismatches cause cascading frontend failures.
• 🧠 Full-stack integration complexity grows non-linearly — allocate explicit integration buffer time in sprint planning.
• 🧠 Explainability (XAI) is not optional in healthcare AI; stakeholders need to understand why a prediction was made, not just what it is.
• 🧠 Performance optimisation (parallel fetching, caching) should be part of the initial architecture, not an afterthought.
• 🧠 User-friendly UI in healthcare is critical — a clinician losing trust in the interface will stop using the tool regardless of model accuracy.
• 🧠 Version-pinning ML dependencies (scikit-learn, SHAP, XGBoost) from the start prevents painful conflicts in later sprints.
7. Tools & Technologies Used
• Frontend : React 18, Recharts, Chart.js, CoreUI Pro (design inspiration), CSS Flexbox / Grid
• Backend : FastAPI (Python 3.11), Pydantic v2, Uvicorn, Python-JOSE (JWT)
• Database : Supabase (PostgreSQL), Supabase Realtime, Row-Level Security
• ML / AI : Scikit-learn (Random Forest, Logistic Regression, K-Fold CV), XGBoost, Prophet (Meta), SHAP (partial)
• Dev Tools : VS Code, Jupyter Notebook, Git, GitHub, Postman, Python venv
• Deployment: Local (dev), planned: Vercel (frontend) + Railway / Render (FastAPI backend)
— End of Sprint Retrospective Report —